## Remarks
# | Review remark | Artifact / Location of issue | Why it is an issue? | How can it be best fixed (with rationale)?
1 | User is not able to unsubscribe | web application | User is able to subscribe to a journal but is not able to unsubscribe. This is lacking functionality that can easily cause frustration for the users. | This is more functional issue. We should add another another button (Unsubscribe) or basically change the label and the action under existing button i.e. If the user is not subscribed the button will display "Subscribe" but if the user is already subscribed, it should display "Unsbscribed" and it should in fact call another REST service in such case.
2 | No error handling | e.g. journal browsing | If the journal is unavailable the application generates unfriendly HTTP 500 error that is not translated to human readable text. It can also disclose internal technical details to pottential hackers. | Each functionality should have proper error handling in case some data is missing or in case of invalid input from the UI. In addition generic error handling/interception (in case of unexpected server error) should be provided.
3 | FE / BE separation | project structure | Project will not scale. FE and BE could be developped by different teams in different locations. Having everything in one project is not only an antipattern but also will be a maintenance nightmare when grows. | BE and FE artifacts should be split into separate projects - ideally separate repositories, so that the work on them can be independent. Other option is to keep them in the same repository - this could speed up initial development and local deployment.
4 | FE modularization | project structure | All the controllers are in one file and it will make maintenance problems - this is not modular. | Each controller should be in a separate JS file and common code should be moved to a separate module(s) e.g. Utils, validation, error handling, dialogs, etc.
5 | BE modularization | project structure | Maintenance and internal dependency spaghetti. | For such project I see the following modules: Model, DTO, DAO / Service API, DAO / Service Impl, REST API, REST Impl, Application. First of all APIs should be separated from implementations as API can be used somewhere else and the implementation may vary. REST API could be documented and sent to the customer. Application module should group all the implementation modules and should build the final webapp image.
6 | Database id instead of business key | project | Depending on autogenrated DB is is never a good idea. In case of data migration or even clustering the DB id for the same object can be different and the whole application will be unusable. | Depend on unique ID of the objects (e.g. UUID) that are managed by the application code, not by the database.
7 | Direct use of JPA repositories | BE structure | Controllers and REST services directly use JPA repositories (DAO layer). Missing service layer may cause maintenance issues. Service layer is also good place to put transactions - not necessarily needed in this project but it might grow, and transactions might be necessary and then the refectoring will be costly. | Add additional service layer that would orchestrate DAO / repositories in an efficient way.
8 | Use of Spring only annotations | REST services | Using Spring annotations for REST services might be dangerous. Not every developer knows Spring REST modules and it could be an issue for newcomers knowing only standards. | Use of standard JAX-RS annotations. It is well documented and maintained by Java community. It is easier to hire people knowing standards than proprietary techs (it's a big exaggerations towards Spring but now we have JAX-RS)
9 | No DTO layer | REST services | We "sell" our JPA objects. It might be inefficient, heavy and dagerous as it can contain internal data we don't want to send over HTTP.
10 | Data filtering on Java side | Service layer e.g. JournalServiceImpl | We contact DB twice + we do filtering on Java side. It is inefficient and might abuse network in case of more data. | We should do filtering on DB side ideally using SQL or JPA QL. This would limit comunication overhead with database and improve performance.
11 | Incomplete DDL | createdb-script.sql | e.g. user name is not unique, publication uuid is not unique. It will cause duplicates easily. | Add uniqueness to some columns that really need to be unique in DB.
12 | Journal with multiple categories | DB structure | If a journal belongs to more than one category (is this possible?) we cannot manage it. | Change DB structure to support multiple categories for a journal.
13 | REST services are stateful | REST services | REST services are strongly tied to HTTP session as they get current user from it. This solution is not scallable as it requires session stickiness or session clustering. | User or publisher id should be a request / path parameter and REST should call another service to check whether currently logged user (based on either session id or security token) has rights to ask for requested data. Session stickiness limit scallability and makes it harder to guarantee high availability.
14 | Application is not deployable | App structure | Mvn does not build WAR for this application which means it is not deployable in any of the application server. I assume that it is done to simplify the test assignment. | We should use proper project structure to build WAR at the end. One for BE and on for FE. If we assume that FE is composed only from static files (including JS) we could deploy it separately from application server in web server for better performance.
15 | No distinction between users and publishers | Logic | Publishers can also subscribe to journals - not sure it's intended.

## Readme
Review remark | Description of the issue found or suggestion for improvement.
Artifact / Location of issue | Which file(s) and method(s) the remark is related to?
Why it is an issue? | Why do you think you are making this remark? What is the rationale/ basis of the remark? Any references you would like to quote?
How can it be best fixed (with rationale)? | What are the changes you suggest to fix the issue or make an improvement?